## Team Brilliance Main Project Ka
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
Sprint Review 4 | https://github.com/COS420-Fall24/TeamB/issues/126 | Product Backlog | [9 empty] | Deliverable 4
Short 4-10 Minute Video showing team progress | https://github.com/COS420-Fall24/TeamB/issues/140 | Product Backlog | [9 empty] | Deliverable 4
CI ( Continuous Integration) | https://github.com/COS420-Fall24/TeamB/issues/127 | Product Backlog | [9 empty] | Deliverable 4
Detailed Technical Design Document | https://github.com/COS420-Fall24/TeamB/issues/139 | Done |  |  |  |  | acetone01, Boubacarmank, Jakob-Sholler, SebAnghel23, yTKONOSINA | BM 40 % / DT 34 % / SA 24 % / Js 2 % | Jakob S. |  |  | Deliverable 4
Design pattern is in Detailed Technical Design | https://github.com/COS420-Fall24/TeamB/issues/141 | Done | [5 empty] | BM 98 % / JS 2 % |  |  |  | Deliverable 4
Sprint backlog 4 | https://github.com/COS420-Fall24/TeamB/issues/128 | In Progress |  |  |  |  | Jakob-Sholler | Js 100 % |  |  |  | Deliverable 4
Usability Testing D4 or D5 | https://github.com/COS420-Fall24/TeamB/issues/142 | Done |  |  |  |  | yTKONOSINA | DT 98 % / JS 2% | Jakob S. |  |  | Deliverable 4
Architecture Design Comments | https://github.com/COS420-Fall24/TeamB/issues/135 | Done |  |  |  |  | Boubacarmank | RS 100 % | Ryan O'Sullivan |  |  | Deliverable 4
Project Board (Kanaban) | https://github.com/COS420-Fall24/TeamB/issues/130 | Done | [5 empty] | RS 20 % / DT 20 % / BM 20 %/ SA 20 % / JS 20 % | Jakob S. |  |  | Deliverable 4
Use Case Diagrams/Models/Descriptions Comments | https://github.com/COS420-Fall24/TeamB/issues/133 | Done |  |  |  |  | acetone01, yTKONOSINA | RS 49 % / DT 49 % / JS 2 % | Jakob S. |  |  | Deliverable 4
SRS Missing Information | https://github.com/COS420-Fall24/TeamB/issues/132 | Done |  |  |  |  | acetone01 | RY 98 % / JS 2 % |  |  |  | Deliverable 4
github | https://github.com/COS420-Fall24/TeamB/issues/129 | Done |  |  |  |  | acetone01, Boubacarmank, Jakob-Sholler, SebAnghel23, yTKONOSINA | BM 20 % / JS 20 % / SA 20 % / RS 20 % / DT 20 % |  |  |  | Deliverable 4
Use Case DIagrams/Models and Descriptions Update(if needed) | https://github.com/COS420-Fall24/TeamB/issues/134 | Done |  |  |  |  | acetone01 |  |  |  |  | Deliverable 4
SRS Comments | https://github.com/COS420-Fall24/TeamB/issues/131 | Done |  |  |  |  | Jakob-Sholler | JS 100 % | Jakob S. |  |  | Deliverable 4
product Backlog | https://github.com/COS420-Fall24/TeamB/issues/125 | Done |  |  |  |  | Boubacarmank | Bm 95 % / JS 5 % | Jakob S. |  |  | Deliverable 4
Domain Model Comments / Feedback | https://github.com/COS420-Fall24/TeamB/issues/136 | Done |  |  |  |  | yTKONOSINA | DT 95% / JS 5% | Jakob S. |  |  | Deliverable 4
New Version of Application ( All Task) | https://github.com/COS420-Fall24/TeamB/issues/138 | Done | [5 empty] | DT 49 % / SA 49 % JS 2 % | Jakob S. |  |  | Deliverable 4
Keeps notes during Sprint | https://github.com/COS420-Fall24/TeamB/issues/119 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 4
Check in on the change(Keep notes during sprint) Halfway | https://github.com/COS420-Fall24/TeamB/issues/120 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 4
Check in on the change (Set times for each point of the sprint) halfway | https://github.com/COS420-Fall24/TeamB/issues/118 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 4
Set Times for each point of the sprint | https://github.com/COS420-Fall24/TeamB/issues/117 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 4