## Team Brilliance Main Project Ka
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, I want interactive exercises for reading code so that I can practice interpreting different programming patterns. | 1 | H | Backlog | 8
2 | As a beginner programmer, I would like to get personalized feedback. | 1 | H | Backlog | 8
3 | As a beginner, I would like to have a step-by-step guide and hints for solutions. | 1 | H | Backlog | 5
4 | As a user, I want to have an intuitive interface for coding elements. | 1 | H | Backlog | 5
8 | As a user, I want to be able to easily understand what I am getting out of each task. | 1 | H | Backlog | 3
12 | As a beginning programmer, I want color-coded code so that each piece of a line of code is more understandable to read. | 1 | H | Backlog | 3
15 | As a beginning programmer, I would want a simple layout within the app so that I would not get overwhelmed with many different pop-ups along with the actual learning code part. | 1 | H | Backlog | 5
19 | As a beginning programmer, I would enjoy positive reinforcement along with positive feedback on my coding skills. | 1 | H | Backlog | 3
10 | As a beginning programmer, I want to be able to use the program offline so that I can learn anytime, anywhere. | 4 | L | Backlog | 8
17 | As a beginning programmer, I would enjoy an incentive to log on every day and practice my skills, perhaps a point system, regardless if it didn't mean anything outside the app. | 3 | L | Backlog | 3
20 | As a beginner programmer, I would like to be able to customize the theme of the program. | 4 | L | Backlog | 3
5 | As a beginner, I would like to have a reference book. | 3 | M | Backlog | 3
6 | As a beginning programmer, I want to be able to test my skill. | 2 | M | Backlog | 5
7 | As a beginning programmer, I want to challenge myself and my programming knowledge. | 2 | M | Backlog | 5
9 | As a user, I want to be able to code without any distractions. | 2 | M | Backlog | 3
11 | As a beginning programmer, I want a quiz/test feature so that I can reinforce the code I am learning. | 2 | M | Backlog | 5
13 | As a beginning programmer, I want to be able to click or use keys to jump to a specific code segment (e.g., a function) so that it is easier to navigate the code. | 2 | M | Backlog | 5
14 | As a beginning programmer, I want some note or annotation feature so that I can have my own explanation above the code, so if I forget, I can see how it works in my own words. | 2 | M | Backlog | 5
16 | As a beginning programmer, I would want the app to provide suggestions on how I can improve on my coding skills. | 3 | M | Backlog | 8
18 | As a beginning programmer, I would want short code review sections from a previous section so I can keep track of where I'm at. | 2 | M | Backlog | 5
Title | URL | Milestone | Deliverable / Sprint | User Story | Story Type | Priority | Estimate (Story Points) | Status
SRS (Address Comments from dev2) | https://github.com/COS420-Fall24/TeamB/issues/73 |  | Deliverable 3 |  |  |  |  | In Progress
Architecture Design First Section ( Package stuff) | https://github.com/COS420-Fall24/TeamB/issues/75 |  | Deliverable 3 |  |  |  |  | In Progress
Github | https://github.com/COS420-Fall24/TeamB/issues/66 |  | Deliverable 3 |  |  |  |  | In Progress
Update Policy.Md | https://github.com/COS420-Fall24/TeamB/issues/115 |  | Deliverable 3 |  |  |  | 0.5 | Quality Checking
Re-organize the folder structure for the repo | https://github.com/COS420-Fall24/TeamB/issues/106 |  | D2 | No |  |  |  | Done
Revised the sprint backlog based on the feedback. | https://github.com/COS420-Fall24/TeamB/issues/116 |  | D2 |  |  |  |  | Done
Set Times for each point of the sprint | https://github.com/COS420-Fall24/TeamB/issues/117 |  | Deliverable 4 |  |  |  |  | Product Backlog
Check in on the change (Set times for each point of the sprint) halfway | https://github.com/COS420-Fall24/TeamB/issues/118 |  | Deliverable 4 |  |  |  |  | Product Backlog
Keeps notes during Sprint | https://github.com/COS420-Fall24/TeamB/issues/119 |  | Deliverable 4 |  |  |  |  | Product Backlog
Check in on the change(Keep notes during sprint) Halfway | https://github.com/COS420-Fall24/TeamB/issues/120 |  | Deliverable 4 |  |  |  |  | Product Backlog
Read Grading Feedback for Deliverable 2 (All) | https://github.com/COS420-Fall24/TeamB/issues/76 |  | Deliverable 3 |  |  | High | 1 | Quality Checking
Architecture Design Description / Justifcation | https://github.com/COS420-Fall24/TeamB/issues/72 |  | Deliverable 3 |  |  |  |  | Quality Checking
Product Backlog Comments Deliverable 2 | https://github.com/COS420-Fall24/TeamB/issues/57 |  | Deliverable 3 |  |  |  |  | Quality Checking
Architecture Design Comments From Deliverable 2) | https://github.com/COS420-Fall24/TeamB/issues/74 |  | Deliverable 3 |  |  |  |  | Quality Checking
Product Backlog (Fill in missing info + update information to reflect current sprint/sprints) | https://github.com/COS420-Fall24/TeamB/issues/58 |  | Deliverable 3 |  |  |  | 0.1 | Quality Checking
merge all active branches | https://github.com/COS420-Fall24/TeamB/issues/107 | [6 empty] | Quality Checking
Usability testing | https://github.com/COS420-Fall24/TeamB/issues/77 |  | Deliverable 3 |  |  |  |  | Quality Checking
Use Case Digrams/ Models and Descriptions Comments | https://github.com/COS420-Fall24/TeamB/issues/60 |  | Deliverable 3 |  |  |  |  | Quality Checking
Use Case Diagrams/Models and Descriptions | https://github.com/COS420-Fall24/TeamB/issues/69 |  | Deliverable 3 |  |  |  |  | Quality Checking
Continuous Integration | https://github.com/COS420-Fall24/TeamB/issues/71 |  | Deliverable 3 |  |  |  |  | Quality Checking
Kanaban(Project Board) | https://github.com/COS420-Fall24/TeamB/issues/59 |  | Deliverable 3 |  |  |  |  | Quality Checking
Sprint Review 4 | https://github.com/COS420-Fall24/TeamB/issues/64 |  | Deliverable 3 |  |  |  |  | Quality Checking
New Version of Application Automated Tests | https://github.com/COS420-Fall24/TeamB/issues/68 |  | Deliverable 3 |  |  |  |  | Quality Checking
Sprint Backlog (Address comments on previous deliverable) | https://github.com/COS420-Fall24/TeamB/issues/62 |  | Deliverable 3 |  |  |  | 0.1 | Quality Checking
New Version of Application 1-10 Minute Progress Video | https://github.com/COS420-Fall24/TeamB/issues/70 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Domain Model (Group Task for Sprint ?) | https://github.com/COS420-Fall24/TeamB/issues/63 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
New Version of application Comments | https://github.com/COS420-Fall24/TeamB/issues/67 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Determine 2-3 Concrete Code Examples | https://github.com/COS420-Fall24/TeamB/issues/111 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Focus Mockups on Interaction loop | https://github.com/COS420-Fall24/TeamB/issues/113 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Prototype Feedback Mechanism | https://github.com/COS420-Fall24/TeamB/issues/112 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
New Version Of Application Core User Story / Feature | https://github.com/COS420-Fall24/TeamB/issues/65 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Use Case Diagrams/ Models and Descriptions. Update | https://github.com/COS420-Fall24/TeamB/issues/61 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
D1 sprint Review Talk about project description issues | https://github.com/COS420-Fall24/TeamB/issues/82 |  | D2 |  |  | Medium |  | Done
Go through And Update any policys, either to clarify or add/ update to where should be quality Checking for example/ Turn into own document on the githhub. | https://github.com/COS420-Fall24/TeamB/issues/88 |  | D2 |  |  | High |  | Done
Use this to redo a prior solution | https://github.com/COS420-Fall24/TeamB/issues/51 |  | D2 |  |  | Medium |  | Done
Create Log in Page ( landing page when not logged in | https://github.com/COS420-Fall24/TeamB/issues/102 |  | D2 |  |  |  |  | Done
Landing Page( When logged In | https://github.com/COS420-Fall24/TeamB/issues/52 |  | D2 |  |  |  |  | Done
10 use case descriptions | https://github.com/COS420-Fall24/TeamB/issues/53 |  | D1 |  |  |  |  | Done
Check SRS comments | https://github.com/COS420-Fall24/TeamB/issues/103 |  | D2 |  |  |  |  | Done
1 Diagram / Model | https://github.com/COS420-Fall24/TeamB/issues/81 |  | D2 |  |  | High |  | Done
Dashboard for app (Interactive Exercises/course material, Progress Tracking, Quizzes, Feedback, Streaks) | https://github.com/COS420-Fall24/TeamB/issues/78 |  | D2 |  |  |  |  | Done
30 minute research on our domain | https://github.com/COS420-Fall24/TeamB/issues/95 |  | D2 |  |  | Medium |  | Done
Prior Solution on this information | https://github.com/COS420-Fall24/TeamB/issues/96 |  | D2 |  |  | Medium |  | Done
Remind Team on Discord Do not break edit history. | https://github.com/COS420-Fall24/TeamB/issues/87 |  | D2 |  |  | High |  | Done
Development Developers Breakdown / assign Need to communicate | https://github.com/COS420-Fall24/TeamB/issues/93 |  | D2 |  |  | High |  | Done
architecture design Description | https://github.com/COS420-Fall24/TeamB/issues/104 |  | D2 |  |  |  |  | Done
30 Minute Research on our Domain | https://github.com/COS420-Fall24/TeamB/issues/97 |  | D2 |  |  | Medium |  | Done
30 minute research on our domain | https://github.com/COS420-Fall24/TeamB/issues/98 |  | D2 |  |  | Medium |  | Done
Complete prior solution on this information | https://github.com/COS420-Fall24/TeamB/issues/99 |  | D2 |  |  | Medium |  | Done
30 minute research on our domain | https://github.com/COS420-Fall24/TeamB/issues/100 |  | D2 |  |  | Medium |  | Done
Architecture Design | https://github.com/COS420-Fall24/TeamB/issues/89 |  | D2 |  |  |  |  | Done
Sprint Backlog Comments | https://github.com/COS420-Fall24/TeamB/issues/90 |  | D2 |  |  |  |  | Done
Quality Check: Update Project Description Document | https://github.com/COS420-Fall24/TeamB/issues/36 | Deliverable 1 | D1 |  |  |  |  | Done
Add install and build process for our app | https://github.com/COS420-Fall24/TeamB/issues/45 | Deliverable 1 | D1 |  |  |  |  | Done
Update Project Description Document | https://github.com/COS420-Fall24/TeamB/issues/27 | Deliverable 1 | D1 |  |  |  |  | Done
Product Backlog Comments | https://github.com/COS420-Fall24/TeamB/issues/84 |  | D2 |  |  |  |  | Done
1 Diagram / Model | https://github.com/COS420-Fall24/TeamB/issues/85 |  | D2 |  |  | High |  | Done
10 Use case Descriptions | https://github.com/COS420-Fall24/TeamB/issues/83 |  | D2 |  |  |  |  | Done
1 Diagram / Model | https://github.com/COS420-Fall24/TeamB/issues/94 |  | D2 |  |  | High |  | Done
User Stories 6-10 (Complete 4-5 Stories) | https://github.com/COS420-Fall24/TeamB/issues/18 | Deliverable 0 | D1 |  |  |  |  | Done
Architecture design diagram | https://github.com/COS420-Fall24/TeamB/issues/91 |  | D2 |  |  |  |  | Done
1 Diagram / Model | https://github.com/COS420-Fall24/TeamB/issues/86 |  | D2 |  |  | High |  | Done
Get user Tests for Prototypes/Mockups | https://github.com/COS420-Fall24/TeamB/issues/92 |  | D2 |  |  |  |  | Done
SRS Document(break down into sections) | https://github.com/COS420-Fall24/TeamB/issues/105 |  | D2 |  |  |  |  | Done
30 minute research of our Domain | https://github.com/COS420-Fall24/TeamB/issues/101 |  |  |  |  | Medium |  | Done
Sprint Review | https://github.com/COS420-Fall24/TeamB/issues/47 | Deliverable 1 | D1
1-10 Non functional Req | https://github.com/COS420-Fall24/TeamB/issues/41 | Deliverable 1 | D1
Github | https://github.com/COS420-Fall24/TeamB/issues/35 | Deliverable 1 | D1
Ui Mockup | https://github.com/COS420-Fall24/TeamB/issues/43 | Deliverable 1 | D1
11-15 Non functional | https://github.com/COS420-Fall24/TeamB/issues/42 | Deliverable 1 | D1
Start Implementation (get base setup ) | https://github.com/COS420-Fall24/TeamB/issues/44 | Deliverable 1 | D1
functional req 1-10 | https://github.com/COS420-Fall24/TeamB/issues/38 | Deliverable 1 | D1
Create Sprint Backlog Document | https://github.com/COS420-Fall24/TeamB/issues/30 | Deliverable 1 | D1
Create Product Backlog | https://github.com/COS420-Fall24/TeamB/issues/32 | Deliverable 1 | D1
Move all user stories into product backlog | https://github.com/COS420-Fall24/TeamB/issues/29 | Deliverable 1 | D1
Update User Story Document | https://github.com/COS420-Fall24/TeamB/issues/26 | Deliverable 1 | D1
functional 11-20 | https://github.com/COS420-Fall24/TeamB/issues/39 | Deliverable 1 | D1
Functional Req 21-30 | https://github.com/COS420-Fall24/TeamB/issues/40 | Deliverable 1 | D1
Add Rubric info into description for all tasks requiring. | https://github.com/COS420-Fall24/TeamB/issues/46 | Deliverable 1 | D1
Address Feedback on problem Statements | https://github.com/COS420-Fall24/TeamB/issues/16 | Deliverable 0
General Overview and Description( Of app) | https://github.com/COS420-Fall24/TeamB/issues/22 | Deliverable 0
create solution 2 | https://github.com/COS420-Fall24/TeamB/issues/9 | Deliverable 0
Create a solution 1 | https://github.com/COS420-Fall24/TeamB/issues/7 | Deliverable 0
yourapp Extra Description Paragraphs | https://github.com/COS420-Fall24/TeamB/issues/24 | Deliverable 0
Yourapp Summary | https://github.com/COS420-Fall24/TeamB/issues/23 | Deliverable 0
Yourapp Taskflow Diagram | https://github.com/COS420-Fall24/TeamB/issues/25 | Deliverable 0
Create Team Name / App Description | https://github.com/COS420-Fall24/TeamB/issues/6 | Deliverable 0
User Stories 1-5 (Complete 4 or 5 user stories) | https://github.com/COS420-Fall24/TeamB/issues/17 | Deliverable 0
Create a Meeting time outside of class | https://github.com/COS420-Fall24/TeamB/issues/5 | Deliverable 0
User stories 11-15 (complete 4-5 User stories) | https://github.com/COS420-Fall24/TeamB/issues/19 | Deliverable 0
create solution 3 | https://github.com/COS420-Fall24/TeamB/issues/10 | Deliverable 0
User Stories 16-20 (Complete 4-5 User stories) | https://github.com/COS420-Fall24/TeamB/issues/20 | Deliverable 0
Sprint Review 4 | https://github.com/COS420-Fall24/TeamB/issues/126 |  | Deliverable 4 |  |  |  |  | Product Backlog
Short 4-10 Minute Video showing team progress | https://github.com/COS420-Fall24/TeamB/issues/140 |  | Deliverable 4 |  |  |  |  | Product Backlog
CI ( Continuous Integration) | https://github.com/COS420-Fall24/TeamB/issues/127 |  | Deliverable 4 |  |  |  |  | Product Backlog
Detailed Technical Design Document | https://github.com/COS420-Fall24/TeamB/issues/139 |  | Deliverable 4 |  |  |  |  | Done
Design pattern is in Detailed Technical Design | https://github.com/COS420-Fall24/TeamB/issues/141 |  | Deliverable 4 |  |  |  |  | Done
Sprint backlog 4 | https://github.com/COS420-Fall24/TeamB/issues/128 |  | Deliverable 4 |  |  |  |  | In Progress
Usability Testing D4 or D5 | https://github.com/COS420-Fall24/TeamB/issues/142 |  | Deliverable 4 |  |  |  |  | Done
Architecture Design Comments | https://github.com/COS420-Fall24/TeamB/issues/135 |  | Deliverable 4 |  |  |  |  | Done
Project Board (Kanaban) | https://github.com/COS420-Fall24/TeamB/issues/130 |  | Deliverable 4 |  |  |  |  | Done
Use Case Diagrams/Models/Descriptions Comments | https://github.com/COS420-Fall24/TeamB/issues/133 |  | Deliverable 4 |  |  |  |  | Done
SRS Missing Information | https://github.com/COS420-Fall24/TeamB/issues/132 |  | Deliverable 4 |  |  |  |  | Done
github | https://github.com/COS420-Fall24/TeamB/issues/129 |  | Deliverable 4 |  |  |  |  | Done
Use Case DIagrams/Models and Descriptions Update(if needed) | https://github.com/COS420-Fall24/TeamB/issues/134 |  | Deliverable 4 |  |  |  |  | Done
SRS Comments | https://github.com/COS420-Fall24/TeamB/issues/131 |  | Deliverable 4 |  |  |  |  | Done
product Backlog | https://github.com/COS420-Fall24/TeamB/issues/125 |  | Deliverable 4 |  |  |  |  | Done
Domain Model Comments / Feedback | https://github.com/COS420-Fall24/TeamB/issues/136 |  | Deliverable 4 |  |  |  |  | Done
New Version of Application ( All Task) | https://github.com/COS420-Fall24/TeamB/issues/138 |  | Deliverable 4 |  |  |  |  | Done
Keeps notes during Sprint | https://github.com/COS420-Fall24/TeamB/issues/119 |  | Deliverable 4 |  |  |  |  | Todo / Sprint Backlog
Check in on the change(Keep notes during sprint) Halfway | https://github.com/COS420-Fall24/TeamB/issues/120 |  | Deliverable 4 |  |  |  |  | Todo / Sprint Backlog
Check in on the change (Set times for each point of the sprint) halfway | https://github.com/COS420-Fall24/TeamB/issues/118 |  | Deliverable 4 |  |  |  |  | Todo / Sprint Backlog
Set Times for each point of the sprint | https://github.com/COS420-Fall24/TeamB/issues/117 |  | Deliverable 4 |  |  |  |  | Todo / Sprint Backlog