## Sprint i
Contribution %
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Jakob Sholler (Product Manager) | Dmitrii Tsutskov (Dev 1) | Sebastian Anghel (Dev 2) | Boubacar Mankirba (Dev 3) | Ryan Osullivan (Design)
1 | As a user, I want interactive exercises for reading code so that I can practice interpreting different programming patterns. | T1.0 | 1. Create a Variety of Programming Pattern Exercises | 1 | High-priority features that are essential for core functionality. | Feature | 8 | 3 | 20 | 20 | 20 | 20 | 20
2 | As a beginner programmer, I would like to get personalized feedback. | T2.0/ T2.1 | 1. Implement Feedback and Explanation System 2.Tailor Feedback to Skill Level |  |  | Feature | 8 | 4 | 20 | 20 | 20 | 20 | 20
3 | As a beginner, I would like to have a step-by-step guide and hints for solutions. | T 3.0/ T 3.1 | 1. Create Step-by-Step Hints for Each Exercise 2. Provide Beginner-Friendly Solutions with Explanations |  |  | Feature | 5 | 2 | 20 | 20 | 20 | 20 | 20
4 | As a user, I want to have an intuitive interface for coding elements. | T 4.0 | 1. Design a User-Friendly Interface |  |  | Design | 5 | 2 | 20 | 20 | 20 | 20 | 20
8 | As a user, I want to be able to easily understand what I am getting out of each task. | T 5.0 | 1. Develop Task Objective and Learning Outcome Display |  |  | Design | 3 | 1 | 20 | 20 | 20 | 20 | 20
12 | As a beginning programmer, I want color-coded code so that each piece of a line of code is more understandable to read. | T 6.0/ T 6.1 | 1. Design a way to be able to track what type code is and color code it (i.e if its a variable it will be 1 color, arrays would show up in another. 2. Implement a way to allow the user to know what each color means. |  |  | Feature | 3 | 1 | 20 | 20 | 20 | 20 | 20
15 | As a beginning programmer, I would want a simple layout within the app so that I would not get overwhelmed with many different pop-ups along with the actual learning code part. | T 7.0 | 1. Avoid or minimize the amount of popups in the interface that exists. |  |  | technical | 5 | 1 | 20 | 20 | 20 | 20 | 20
19 | As a beginning programmer, I would enjoy positive reinforcement along with positive feedback on my coding skills. | T 8.0 / T 8.1 / T 8.2 | 1.Define feedback criteria 2. create a system to provide feedback to user. 3. Implement the positive reinforcment features. |  |  | technical | 3 | 2 | 20 | 20 | 20 | 20 | 20
20 | Prepare Zenhub Kanban | T 20.1/20.2 | 1. Complete Sprint 1 Backlog 2. Complete Product Backlog |  |  | Knowledge Area | 1 | 1 | 20 | 20 | 20 | 20 | 20
21 | Make mockups for UI navigation | T 21.1/21.2 | 1. Design visual mockups 2. Add project requirements |  |  | Knowledge Area | 1 | 1 | 20 | 20 | 20 | 20 | 20
6 | As a beginning programmer, I want to be able to test my skill. | T 9.0 | 1. Implement Skill Testing Features | 2 | Medium-priority features that enhance user experience. | technical | 5 | 0 | 0 | 0 | 0 | 0 | 0
7 | As a beginning programmer, I want to challenge myself and my programming knowledge. | T 10.0 | 1. Design some sort of ranking system to allow for a way to be able to challenge themselves |  |  | technical | 5 | 0 | 0 | 0 | 0 | 0 | 0
9 | As a user, I want to be able to code without any distractions. | T 11.0 | 1. Create a Distraction-Free Interface |  |  | design | 3 | 0 | 0 | 0 | 0 | 0 | 0
11 | As a beginning programmer, I want a quiz/test feature so that I can reinforce the code I am learning. | T 12.0 | 1. Develop Quiz/Test Functionality |  |  | technical | 5 | 0 | 0 | 0 | 0 | 0 | 0
13 | As a beginning programmer, I want to be able to click or use keys to jump to a specific code segment (e.g., a function) so that it is easier to navigate the code. | T 13.0 | 1. Enable Code Segment Navigation |  |  | technical | 5 | 0 | 0 | 0 | 0 | 0 | 0
14 | As a beginning programmer, I want some note or annotation feature so that I can have my own explanation above the code, so if I forget, I can see how it works in my own words. | T 14.0 | 1. Create tools to allow for annotation/note keeping. |  |  | feature | 5 | 0 | 0 | 0 | 0 | 0 | 0
18 | As a beginning programmer, I would want short code review sections from a previous section so I can keep track of where I'm at. | T 15.0 | 1. Implement Code Review Summary |  |  | feature | 5 | 0 | 0 | 0 | 0 | 0 | 0
22 | Create documents for D2 | T 22.1/ T 22.2 | 1. Create use case document 2. Usability Testing documents and results |  |  | Knowledge Area | 2 | 0
5 | As a beginner, I would like to have a reference book. | T 16.0 | 1. Provide a Reference Section | 3 | Additional medium-priority features and enhancements. | feature | 3 | 0 | 0 | 0 | 0 | 0 | 0
16 | As a beginning programmer, I would want the app to provide suggestions on how I can improve on my coding skills. | T 17.0 | 1. Create some sort of algorithm that can suggest information based on the users current information gather on the user(work done on the app etc) |  |  | feature | 8 | 0 | 0 | 0 | 0 | 0 | 0
17 | As a beginning programmer, I would enjoy an incentive to log on every day and practice my skills, perhaps a point system, regardless if it didn't mean anything outside the app. | T 18.0 | 1. Introduce a Point System and Daily Rewards |  |  | feature | 3 | 0 | 0 | 0 | 0 | 0 | 0
10 | As a beginning programmer, I want to be able to use the program offline so that I can learn anytime, anywhere. | T 19.0 | 1. Implement a way to download problems and topics offline. | 4 | Low-priority features or those requiring more development effort. | technical | 8 | 0 | 0 | 0 | 0 | 0 | 0

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657