## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, I want interactive exercises for reading code so that I can practice interpreting different programming patterns. | 1 | H | Backlog | 8
2 | As a beginner programmer, I would like to get personalized feedback. | 1 | H | Backlog | 8
3 | As a beginner, I would like to have a step-by-step guide and hints for solutions. | 1 | H | Backlog | 5
4 | As a user, I want to have an intuitive interface for coding elements. | 1 | H | Backlog | 5
5 | As a beginner, I would like to have a reference book. | 3 | M | Backlog | 3
6 | As a beginning programmer, I want to be able to test my skill. | 2 | M | Backlog | 5
7 | As a beginning programmer, I want to challenge myself and my programming knowledge. | 2 | M | Backlog | 5
8 | As a user, I want to be able to easily understand what I am getting out of each task. | 1 | H | Backlog | 3
9 | As a user, I want to be able to code without any distractions. | 2 | M | Backlog | 3
10 | As a beginning programmer, I want to be able to use the program offline so that I can learn anytime, anywhere. | 4 | L | Backlog | 8
11 | As a beginning programmer, I want a quiz/test feature so that I can reinforce the code I am learning. | 2 | M | Backlog | 5
12 | As a beginning programmer, I want color-coded code so that each piece of a line of code is more understandable to read. | 1 | H | Backlog | 3
13 | As a beginning programmer, I want to be able to click or use keys to jump to a specific code segment (e.g., a function) so that it is easier to navigate the code. | 2 | M | Backlog | 5
14 | As a beginning programmer, I want some note or annotation feature so that I can have my own explanation above the code, so if I forget, I can see how it works in my own words. | 2 | M | Backlog | 5
15 | As a beginning programmer, I would want a simple layout within the app so that I would not get overwhelmed with many different pop-ups along with the actual learning code part. | 1 | H | Backlog | 5
16 | As a beginning programmer, I would want the app to provide suggestions on how I can improve on my coding skills. | 3 | M | Backlog | 8
17 | As a beginning programmer, I would enjoy an incentive to log on every day and practice my skills, perhaps a point system, regardless if it didn't mean anything outside the app. | 3 | L | Backlog | 3
18 | As a beginning programmer, I would want short code review sections from a previous section so I can keep track of where I'm at. | 2 | M | Backlog | 5
19 | As a beginning programmer, I would enjoy positive reinforcement along with positive feedback on my coding skills. | 1 | H | Backlog | 3
20 | As a beginner programmer, I would like to be able to customize the theme of the program. | 4 | L | Backlog | 3
Sprint Number:
Sprint 1: High-priority features that are essential for core functionality.
Sprint 2: Medium-priority features that enhance user experience.
Sprint 3: Additional medium-priority features and enhancements.
Sprint 4: Low-priority features or those requiring more development effort.
Story Priority:
H (High): Crucial features necessary for the app's success.
M (Medium): Important features that improve usability and learning effectiveness.
L (Low): Nice-to-have features that enhance user satisfaction but are not critical.
Story Status:
All stories are currently in Backlog status.
Story Points:
3 Points: Low effort and complexity.
5 Points: Moderate effort and complexity.
8 Points: High effort and complexity.
Explanation of Assignments:
Sprint 1 (High Priority):
ID 1: Interactive exercises for reading code—core to practicing code interpretation.
ID 2: Personalized feedback—essential for user learning and growth.
ID 3: Step-by-step guide and hints—helps users understand solutions.
ID 4: Intuitive interface—crucial for user engagement and ease of use.
ID 8: Understanding task outcomes—enhances clarity and purpose.
ID 12: Color-coded code—improves code readability and comprehension.
ID 15: Simple layout—prevents user overwhelm and distraction.
ID 19: Positive reinforcement and feedback—boosts motivation and confidence.
Sprint 2 (Medium Priority):
ID 6: Ability to test skills—allows users to assess their progress.
ID 7: Challenge themselves—promotes deeper learning.
ID 9: Code without distractions—enhances focus during coding.
ID 11: Quiz/test feature—reinforces learning through assessment.
ID 13: Navigate code segments—improves usability and navigation.
ID 14: Note/annotation feature—personalizes learning and aids memory.
ID 18: Short code review sections—helps users track their learning path.
Sprint 3 (Medium Priority):
ID 5: Reference book—provides additional learning resources.
ID 16: Suggestions for improvement—guides users on enhancing skills.
ID 17: Incentive to log on daily—encourages consistent practice.
Sprint 4 (Low Priority):
ID 10: Use the program offline—enables access anytime, anywhere, with higher complexity.
ID 20: | Ability to customize App theme—personalize experience/more connected to the app

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657