## Team Brilliance Main Project Ka
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
Read Grading Feedback for Deliverable 2 (All) | https://github.com/COS420-Fall24/TeamB/issues/76 | Done | High |  | 1 | 1 | acetone01, Boubacarmank, Jakob-Sholler, SebAnghel23, yTKONOSINA | JS 20%/ RS 20% / BM 20% / SA 20% / DT 20% |  |  | 2024-10-30 | Deliverable 3
Architecture Design Description / Justifcation | https://github.com/COS420-Fall24/TeamB/issues/72 | Done |  |  |  |  | Boubacarmank | Bm 95% / Js 5% | Jakob S. |  | 2024-10-04 | Deliverable 3
New Version Of Application Core User Story / Feature | https://github.com/COS420-Fall24/TeamB/issues/65 | Done |  |  |  |  | acetone01 | __ 90 % / __ 10 % |  |  |  | Deliverable 3
Architecture Design First Section ( Package stuff) | https://github.com/COS420-Fall24/TeamB/issues/75 | Done |  |  |  |  | acetone01 | RS 95 % / Js 5 % |  |  | 2024-11-04 | Deliverable 3
New Version of Application Automated Tests | https://github.com/COS420-Fall24/TeamB/issues/68 | Done |  |  |  |  | yTKONOSINA | DT 90%/ __ 10% |  |  | 2024-11-06 | Deliverable 3
Product Backlog Comments Deliverable 2 | https://github.com/COS420-Fall24/TeamB/issues/57 | Done |  |  |  |  | Boubacarmank | BM 95%/ JS 5% | Jakob S. |  | 2024-11-02 | Deliverable 3
Architecture Design Comments From Deliverable 2) | https://github.com/COS420-Fall24/TeamB/issues/74 | Done |  |  |  |  | Boubacarmank | Bm 95% / JS 5% | Jakob S. |  | 2024-11-02 | Deliverable 3
Use Case Digrams/ Models and Descriptions Comments | https://github.com/COS420-Fall24/TeamB/issues/60 | Done |  |  |  |  | acetone01 |  | Jakob S. |  | 2024-11-02 | Deliverable 3
Use Case Diagrams/Models and Descriptions | https://github.com/COS420-Fall24/TeamB/issues/69 | Done |  |  |  |  | yTKONOSINA |  |  |  | 2024-11-04 | Deliverable 3
Kanaban(Project Board) | https://github.com/COS420-Fall24/TeamB/issues/59 | Done | [8 empty] | 2024-11-02 | Deliverable 3
Usability testing | https://github.com/COS420-Fall24/TeamB/issues/77 | Done |  |  |  |  | yTKONOSINA | __ 90 % / __ 10 % |  |  | 2024-11-06 | Deliverable 3
Continuous Integration | https://github.com/COS420-Fall24/TeamB/issues/71 | Done |  |  |  |  | yTKONOSINA | DT 80 % / SA 15 % / JS 5 % | Jakob S. |  | 2024-11-06 | Deliverable 3
New Version of Application 1-10 Minute Progress Video | https://github.com/COS420-Fall24/TeamB/issues/70 | Done |  |  |  |  | SebAnghel23 | SA 99 % / JS 1 % | Jakob S. |  | 2024-11-08 | Deliverable 3
Github | https://github.com/COS420-Fall24/TeamB/issues/66 | Done |  |  |  |  | acetone01, Boubacarmank, Jakob-Sholler, SebAnghel23, yTKONOSINA | BM 20 % / JS 20 % / SA 20 % / RO 20 % / DT 20% | Jakob S. |  | 2024-11-08 | Deliverable 3
Update Policy.Md | https://github.com/COS420-Fall24/TeamB/issues/115 | Quality Checking |  |  | 0.5 |  | Jakob-Sholler | JS 90% /SA 10% | Sebastian A. |  | 2024-11-03 | Deliverable 3
SRS (Address Comments from dev2) | https://github.com/COS420-Fall24/TeamB/issues/73 | Done |  |  |  |  | acetone01 | RS 95 % Js 5 % | Jakob S. |  | 2024-11-02 | Deliverable 3
Product Backlog (Fill in missing info + update information to reflect current sprint/sprints) | https://github.com/COS420-Fall24/TeamB/issues/58 | Quality Checking |  |  | 0.1 | 0.1 | Jakob-Sholler | JS 90% / __ 10% |  |  | 2024-11-03 | Deliverable 3
Sprint Review 4 | https://github.com/COS420-Fall24/TeamB/issues/64 | Quality Checking |  |  |  |  | Jakob-Sholler |  |  | 2024-10-31 | 2024-11-07 | Deliverable 3
New Version of application Comments | https://github.com/COS420-Fall24/TeamB/issues/67 | Quality Checking |  |  |  |  | Jakob-Sholler | JS 90% / __ 10% |  |  | 2024-11-02 | Deliverable 3
Domain Model (Group Task for Sprint ?) | https://github.com/COS420-Fall24/TeamB/issues/63 | Done |  |  |  |  | SebAnghel23 | SA 95 % / JS 5 % | Jakob S. |  | 2024-11-06 | Deliverable 3
Use Case Diagrams/ Models and Descriptions. Update | https://github.com/COS420-Fall24/TeamB/issues/61 | Done |  |  |  |  | Boubacarmank | __ 90 % / __ 10 % |  |  | 2024-11-05 | Deliverable 3
Sprint Backlog (Address comments on previous deliverable) | https://github.com/COS420-Fall24/TeamB/issues/62 | Done |  |  | 0.1 | 0.1 | Jakob-Sholler | JS 90%/ __ 10% |  | 2024-10-21 | 2024-11-02 | Deliverable 3
Determine 2-3 Concrete Code Examples | https://github.com/COS420-Fall24/TeamB/issues/111 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 3
Focus Mockups on Interaction loop | https://github.com/COS420-Fall24/TeamB/issues/113 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 3
Prototype Feedback Mechanism | https://github.com/COS420-Fall24/TeamB/issues/112 | Todo / Sprint Backlog | [5 empty] | __ 90 % / __ 10 % |  |  |  | Deliverable 3
Missing FIles for Deliverable 3 | https://github.com/COS420-Fall24/TeamB/pull/123 | Done